## Tabelle1
Time Log | Software Projekt 2018/2019
|  |  |  | Name: | Patrick Gautheret (username on GitHub: ElectrifyPowr)
|  |  |  | Student ID / Matrikelnummer: | 3125301
Week | Calendar Week | From | To | Hours | Activities
1 | 40 | 2018-10-04 | 2018-10-10 | 3 | Decision of which topic the team will program Start working on Vision Document with the team
2 | 41 | 2018-10-11 | 2018-10-17 | 11 | Finishing Vision Document with the team Setting up GitHub project Setting up Trello for the team Further discussing & gathering ideas for the game Working on Risk List Starting test project to try out different things (creating a panel, including game loop)
3 | 42 | 2018-10-18 | 2018-10-24 | 9 | Further acquiring knowledge about the AI algorithm that is being used for the game Finishing Requirements Specifications with the group Further developing the ideas for the game Further development of test project: * Changing background of JPanel * Creating a basic avatar (a simple square) * Moving the avatar with user input (with arrow keys on keyboard)
4 | 43 | 2018-10-25 | 2018-10-31 | 10.5 | Further development of Architectural Notebook, including the domain model with layers, architectural mechanisms, class diagram further discussions with group members on design & logic of game Further development of test project: * including collision detection with borders of frame when moving with avatar * starting of the map builder logic
5 | 44 | 2018-11-01 | 2018-11-07 | 14 | Further development of test project: * included map-elements * collision detection with map-elements & avatar * window design according to Kasparas’ specifications * fixed some bugs with collision detection finished updating product backlog
6 | 45 | 2018-11-08 | 2018-11-14
7 | 46 | 2018-11-15 | 2018-11-21
8 | 47 | 2018-11-22 | 2018-11-28
9 | 48 | 2018-11-29 | 2018-12-05
10 | 49 | 2018-12-06 | 2018-12-12
11 | 50 | 2018-12-13 | 2018-12-19
12 | 51 | 2018-12-20 | 2018-12-26
13 | 52 | 2018-12-27 | 2019-01-02
14 | 1 | 2019-01-03 | 2019-01-09
15 | 2 | 2019-01-10 | 2019-01-16
16 | 3 | 2019-01-17 | 2019-01-23
Formulas:
To = [From]+6
From = [From, row above]+7