## Risks
trAIner Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2018-10-11 | Wrong development platform | It is possible that the chosen development platform might be short of some libraries that could make the development process a lot easier. | Resource | 3 | 60% | 1.8 |  | Doing some research beforehand to make sure the most suitable development platform was chosen
2 | 2018-10-11 | AI computing speed | The artificial intelligence logic might have to process a lot, which in turn could slow down the user interface & therefore affect the user experience | Technical | 3 | 20% | 0.6 |  | Making sure that some processes & computations will be handled in background threads
3 | 2018-10-11 | Fun factor | It is possible that the game becomes boring after playing a certain amount of time | Business | 4 | 50% | 2 |  | Develop a lot of different levels/maps & making sure the leaderboards won’t stay the same over a long period of time
4 | 2018-10-11 | Team size & knowledge | A small might not accomplish as much as a bigger team, however, the bigger the team the more misunderstandings might occur. Also the knowledge of the team members on certain algorithms, AI, structured coding might cause problems | Technical | 3 | 30% | 0.9 |  | Team members should understand at least 80% of the code & if problems occur team members should always help each other out.
5 | 2018-10-11 | Schedule & budget | To develop certain depths & testing of a game there is no question that a lot of time is required & all the team members also have other projects to work on. Also, to include the leaderboard for multiplayers, a server might be necessary, which can not be paid since there is no funding for this project. | Schedule, Business, Resource | 3 | 40% | 1.2 |  | Each team member should have a flexible schedule so that each week they can make progress with the project. Another solution should be found for a possible server.
6 | 2018-10-11 | Inadequate specification | It is possible that some team members have different ideas on how the game should work & look due to inadequate specification | Business | 3 | 30% | 0.9 |  | Specify a very complete description of the game with the help of use cases & team member discussions of the vision
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
Note on E2: rbalduino: Risk Type = Direct or Indirect Resource Business Technical Schedule
Note on F2: mbarnard: Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: mbarnard: Probability is the percentage chance that a risk will occur.
Note on H2: mbarnard: Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.