## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a player I want to create an empty map where I could later put building blogs in order to complete my custom map | 5 | 10
2 | As a player I want to have a side navigation bar so that I could select different building blocks that could be easily dragged and dropped on to the map | 5 | 5
3 | As a player I want to easily place the building blocks on to the map by dragging and dropping them | 5 | 10 |  |  | The map also will contain the starting point
4 | As a player I want to save my created map so I could train my AI on it | 5 | 5
5 | As a player I want to load any of my saved maps | 5 | 2
6 | As a player I want to be able to edit my already created maps | 3 | 2
7 | As a player I want to start training the AI on a preloaded map whenever I press play | 5 | 30
8 | As a player I can adjust the learning parameters of the AI | 4 | 15
9 | As a player I want the AI to 'mutate' automatically if it doesn't react the goal | 5 | 20
10 | As a player I want my AI to be able to compete on a pre-built challange map in order to get upgrades | 5 | 25
11 | As a player I want to be rated whenever I finish a pre-built challenge map and be put on a scoreboard | 3 | 10
12 | As a player I want to receive powerups after successfully completing challanges | 2 | 5 |  |  | A reward could be an increase of the population size
w

## Sprint 1
Sprint 1
Starts | 2017-10-28
Ends | 2017-11-25
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required